## John Lockwood
Date	Time Spent	What
07/25/15	3 hours	Initial research and project creation
07/26/15	3 hours	Continue preliminary work on Eve
08/01/15	3 hours	Initial Bitbucket commit. unit tests; work on idea project; test project generally
08/02/15	2 hours	Create spec, Postman Testing
08/03/15	.5 hour	Add Team Entity and Test; create hours.
08/06/15	.5 hour	Wrestle with an Eve configuration issue
08/08/15	3 hours	Solve Eve configuration issue. Preliminary bootstrap styling. Fix paths to static and template files.
08/09/15	1.75 hours	Rework packages yet again. Tests still hosed at this point. Initial work on authentication, using alguitos as test endpoint.
08/14/15	3 hours	Begin writing auth tests. Write function to encode basic auth headers. Exercise Docstring mojo Remove settings.py in favor of inline settings in App. Preliminary Team+Password auth class.
08/15/15	3 hours	Demo Ipython notebooks for testing/documentation. Rework people resource to begin using it as “User”.
08/16/15	3 hours	Create common unit test / integration test helper. Begin work on “integration test”, SetupDemo. Lot of good learning.
08/21/15	.5 hour	Attempt to get authentication to work cleanly for superuser (site admin, god). Moving in different direction.
08/22/15	3 hours	Set up Jinja templates including default layout, jquery version of active tab logic, and demo Flask session use, preliminary login and register pages. Rework jquery version of active tab logic to Jinja to avoid flashing. Create “controllers” package (really Jinja views); begin moving view code there.
08/23/15	2.5 hours	Incorporate Angular.js, with basic routing in place. Still deciding on Angular Single Page App versus Jinja.
08/24/15	1 hour	Begin work on registration data model unit test and class.