## John Lockwood
Date	Time Spent	What
07/25/15	3 hours	Initial research and project creation
07/26/15	3 hours	Continue preliminary work on Eve
08/01/15	3 hours	Initial Bitbucket commit. unit tests; work on idea project; test project generally
08/02/15	2 hours	Create spec, Postman Testing
08/03/15	.5 hour	Add Team Entity and Test; create hours.
08/06/15	.5 hour	Wrestle with an Eve configuration issue
08/08/15	3 hours	Solve Eve configuration issue. Preliminary bootstrap styling. Fix paths to static and template files.
08/09/15	1.75 hours	Rework packages yet again. Tests still hosed at this point. Initial work on authentication, using alguitos as test endpoint.
08/14/15	3 hours	Begin writing auth tests. Write function to encode basic auth headers. Exercise Docstring mojo Remove settings.py in favor of inline settings in App. Preliminary Team+Password auth class.
08/15/15	3 hours	Demo Ipython notebooks for testing/documentation. Rework people resource to begin using it as “User”.
08/16/15	3 hours	Create common unit test / integration test helper. Begin work on “integration test”, SetupDemo. Lot of good learning.
08/22/15	.5 hour	Attempt to get authentication to work cleanly for superuser (site admin, god). Moving in different direction.
08/23/15	1.75 hours	Set up Jinja templates including default layout, jquery version of active tab logic, and demo Flask session use, preliminary login and register pages.